## Defect Tracking Log
DEFECT TRACKING LOG
Project Name | PHPTravels
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 2022-12-23 | Tasleem | From user login,unable to add fund using paypal.On clicking the paypal button,it does not move to next page. | Executing/Controlling | Testing | Medium |  |  |  | New |  |  |  |  | New
2 | 2022-12-24 | Tasleem | From user login and agent login,unable to add fund using bank transfer.On clicking the paybutton the next page appears which does not show any button for doing payment | Executing/Controlling | Testing | High |  |  |  | New |  |  |  |  | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 2022-12-24 | Tasleem | From user login and agent login,Profile also gets updated when both first and last name is deleted which should not happen | Executing/Controlling | Testing | Medium |  |  |  | New |  |  |  |  | In Progress | Medium | Initiating | Concept
4 | 2022-12-26 | Tasleem | From user login and agent login,click transfers link,click the car details,404 error displayed. | Executing/Controlling | Testing | Medium |  |  |  | New |  |  |  |  | Completed | Low | Planning | Requirements
5 | 2022-12-26 | Tasleem | From user login and agent login,click transfers link,click the cars displayed in the transfer page,it takes me to home page for hotel booking instead of transfer booking. | Executing/Controlling | Testing | High |  |  |  | New | [6 empty] | Executing/Controlling | Design
6 | 2022-12-28 | Tasleem | From user login and agents login,click hotels link,booking can be done with by giving alphabets in phone number .which should bot be allowed. | Executing/Controlling | Testing | High |  |  |  | New | [6 empty] | Closing | Development
7 | 2022-12-28 | Tasleem | From agent login,profile is updated without first name and last name.Hotel booking is done by clicking on hotels.Booking happens without name which should not be allowed. | Executing/Controlling | Testing | Medium |  |  |  | New | [7 empty] | Testing
8 | 2022-12-29 | Tasleem | The submission form in visa link gets submitted even if no details are entered. | Executing/Controlling | Testing | Medium |  |  |  | New | [7 empty] | Documentation and Training
9 | 2022-12-29 | Tasleem | From agent login, confirmed tab shows incorrect spelling as confrimed. | Executing/Controlling | Testing | Medium |  |  |  | New | [7 empty] | Deployment
10 | 2023-01-16 | Tasleem | From agent login,click bookings,the bookings are displayed.click invoice,a new page is opened which shows the invoice.Click account and click logout.Logout occurs and the login page is displayed.Click the tab from which invoice was clicked.Click on any link,it works,logout has not happened. | Executing/Controlling | Testing | Medium |  |  |  | New | [7 empty] | Post-Deployment
11 | 2023-01-16 | Tasleem | From supplier login,Click the link Bookings, an error is displayed. | Executing/Controlling | Testing | Medium |  |  |  | New
12 | 2023-01-17 | Tasleem | From supplier login,Click the link Bookings, an error is displayed. | Executing/Controlling | Testing | Medium |  |  |  | New
13 | 2023-01-18 | Tasleem | From supplier login,the flights module link in missing . | Executing/Controlling | Testing | Medium |  |  |  | New
14 | 2023-01-18 | Tasleem | From supplier login,the visa module link in missing . | Executing/Controlling | Testing | Medium |  |  |  | New
15
16
17
18
Note on E9: ====== ID#AAAAjq3Whi4 Julie Arnold (2022-11-12 10:55:31) Choose from the drop down box.
Note on F9: ====== ID#AAAAjq3WhjA John Casey (2022-11-12 10:55:31) Choose from the drop down box.
Note on G9: ====== ID#AAAAjq3Whi8 Julie Arnold (2022-11-12 10:55:31) Choose from the drop down list
Note on K9: ====== ID#AAAAjq3Whi0 Julie Arnold (2022-11-12 10:55:31) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).